## Sheet1
Churn_prediction_Model
DOMAIN NAME: | Machine Learning
INTERN NAME: | Shashank Sharma
PROJECT NAME: | Customer Churn prediction in Telecommunication Company
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2023-11-26
Lesson Number | Lesson Description | Applicable Phase | What Worked Well | What Could Have Been Done Differently | Recommendations for Future
1 | Data Collection | Planning | Data collection was provided beforehand in the Google form | I encountered challenges in data cleaning and had some missing data issues that delayed the project. | Plan for data cleaning and quality assurance in the early stages of the project.
2 | Model Selection | Development | I eperimented with various machine learning algorithms and found that Catboost perfromed best. | I was allocated moderate time to work on the project.
3 | Feature Engineering | Development | Feature engineering, including Upsampling of categorical variables, significantly improved model performance.
4 | Model Evaluation | Testing | I conducted random forest classification and assessed the model using multiple metrics, providing a comprehensive understanding of its performance. |  | Include a range of evaluation metrics to assess model performance comprehensively.
5 | Deployment | Deployment | The model deployment process was smooth, and it works well.
This Lessons Learned Log captures key insights from my Customer Churn Prediction project, highlighting what worked well, what could have been done differently, and recommendations my future projects.